## Slide 1
MS4SSA Rwanda Node:
Implementation
May 29-30, 2018
MS4SSA nodes conference
Notes: The presentation gives a brief description of the initiative to improve the teaching and learning of Maths and Science in Sub-Saharan Africa (MS4SSA). We believe that In Rwanda, the project will contribute to support the implementation of the new curriculum (Competence-Based Curriculum) in place in our schools. The WB launched this initiative in May, this year when the proposal for the public institutions has passed. The implementation is requiring joint-effort from all institutions engaged in training teacher both in-service and pre-service teachers. These are REB, URCE and AIMS. MINEDUC is coordinating the activities.

## Slide 2: Contents
2
Country Implementation plan of the pilot
Training of teachers. Changes.
Partners: Roles and responsibilities
Lessons learnt and challenges

## Slide 3: Country’s implementation plan
2
Pilot proposed in 30 schools. One school in each district. 6excellent (20%), 12 (40%) Intermediate (40%), 12 (40%) 12YBE. Selected schools have a room with 100 laptops, projector, Internet,
Starting in April 2018 and initially focusing on S1 (Grade 7) in Maths, Physics, Chemistry and Biology). Pilot to last for 2 years (up to end of 2019 including reporting)

## Slide 4: Country implementation plan (Cont.)
District 2:
6 schools:
24 teachers)
16
Training of ToTs (Pedagogy) (2-5 February)
Trainers : NCJCTL+WPI
ToTs: 37 teachers+12 URCE staff+ 2 AIMS staff
Step 2
Step 3
Equipment; test to students
Visit to schools; Monitoring and evaluation
Identification of Budget sources; Needs assessment, Adapt MS4SSA to Rwanda country curriculum,Validation of aligned materials; selection of schools, selection of teachers
Step 1
Step 4
Training of Teachers (S1: Pedagogy, Maths and Science ):
23-31 March 2018
Teachers: 120 teachers (including the ToTs)
Trainers: WPI+NJCTL+Gambia+URCE+AIMS+ToTs

## Slide 5
New pedagogy (Direct instruction, Direct Assessment, socio constructivism)
Project-based learning (material science, Robotics, solar energy, water filters, 3D printing)
S1 Content (Challenging topics)
ICT integration
Training of teachers
Changes in teachers (see Videos)
https://drive.google.com/file/d/1ygQeWqlGL7sj5keHp0fe0r3m5BUCs_5u/view?usp=sharing
https://drive.google.com/file/d/1UEqKWnt29NvnjeDP9qmM9l1Jd-kpgB4o/view?usp=sharing
Notes: The presentation gives a brief description of the initiative to improve the teaching and learning of Maths and Science in Sub-Saharan Africa (MS4SSA). We believe that In Rwanda, the project will contribute to support the implementation of the new curriculum (Competence-Based Curriculum) in place in our schools. The WB launched this initiative in May, this year when the proposal for the public institutions has passed. The implementation is requiring joint-effort from all institutions engaged in training teacher both in-service and pre-service teachers. These are REB, URCE and AIMS. MINEDUC is coordinating the activities.

## Slide 6: Partners: Roles and Responsibilities
14
MINEDUC
Overall Coordination/ Facilitation
URCE (ACEITLMS)
Core pedagogical team.
AIMS
Financial management
REB
Training master trainers
Training master trainers
MCF
WPI+NJCTL
+WB
Selection of schools
Support with curriculum adaptation both maths and Physics
Overall budget
Develop MS4SSA content
Support with adapting the curricula to the Rwanda context and also in teaching the master trainers.

## Slide 7
Problem of projectors (One is not enough)
Alignment of MS4SSA to the country curriculum.
Misalignment of Biology content
Instruments for evaluation of the impact
Strengthening the trainers
Lessons learnt
Sources of budget (Lucky to have MCF)
Collaboration with REB, MINEDUC: Facilitate the communication with headmasters, get the teachers for training, etc
Test of teachers: The test happened at the schools instead of bring them to the Capital city.---------> Low cost
Challenges
Notes: The presentation gives a brief description of the initiative to improve the teaching and learning of Maths and Science in Sub-Saharan Africa (MS4SSA). We believe that In Rwanda, the project will contribute to support the implementation of the new curriculum (Competence-Based Curriculum) in place in our schools. The WB launched this initiative in May, this year when the proposal for the public institutions has passed. The implementation is requiring joint-effort from all institutions engaged in training teacher both in-service and pre-service teachers. These are REB, URCE and AIMS. MINEDUC is coordinating the activities.